## Project Plan
Level | Task Name | Status | % Complete | Start Date | End Date | Duration | Predecessors | Owner | Priority | Total Float | Critical ? | On Hold? | Not Applicable? | Baseline Start | Baseline Finish | Variance | Schedule Health | Comments | Assigned To
0 | Zycus - UniSan S2P Implementation | In Progress | 0.44 | 2026-02-11 | 2026-10-09 | 170 |  |  |  | 0 | TRUE |  |  | 2026-05-03 | 2026-05-20 | -2 | Red
1 | Contract Sign Off | Completed | 1 | 2026-02-11 | 2026-02-11 | 1 |  |  |  | 169 |  |  |  | 2026-02-11 | 2026-02-11 | 0 | Green
1 | Project Initiation and Data Gathering | Completed | 1 | 2026-02-19 | 2026-03-17 | 18 |  |  |  | 146 |  |  |  | 2026-02-12 | 2026-03-18 | 1 | Green
1 | Configuration Validation & Documentation | Completed | 1 | 2026-03-13 | 2026-04-27 | 32 |  |  |  | 117 |  |  |  | 2026-03-13 | 2026-04-28 | 1 | Green
1 | Single Sign On and User details Integration | Completed | 1 | 2026-03-13 | 2026-04-16 | 25 |  |  |  | 124 |  |  |  | 2026-03-13 | 2026-04-16 | 0 | Green
1 | Contract Management with Basic Setup | Completed | 1 | 2026-04-23 | 2026-05-05 | 8 |  |  |  | 112 |  |  |  | 2026-04-23 | 2026-05-05 | 0 | Green
1 | Supplier Information Management with Integration | Completed | 1 | 2026-04-23 | 2026-05-15 | 16 |  |  |  | 104 |  |  |  | 2026-04-23 | 2026-05-20 | 3 | Green
1 | User Acceptance Testing (UAT) Phase I | Completed | 1 | 2026-05-04 | 2026-05-20 | 13 |  |  |  | 101 |  |  |  | 2026-05-04 | 2026-06-16 | 18 | Green
1 | UAT Completion I | Completed | 1 | 2026-05-20 | 2026-05-20 | 0 | 107 |  |  | 69 |  |  |  | 2026-05-20 | 2026-05-20 | 0 | Green
1 | Value KPI Sign-off | Completed | 1 | 2026-05-18 | 2026-05-18 | 0 | 91, 105 |  |  | 101 |  |  |  | 2026-05-20 | 2026-05-20 | 2 | Red |  | UniSan Project Group, Zycus Product Specialist, Zycus Project Manager
1 | Training Phase I | In Progress | 0.77 | 2026-05-19 | 2026-05-28 | 7 |  |  |  | 96 |  |  |  | 2026-05-19 | 2026-06-22 | 17 | Green
1 | Training Completion | Completed | 1 | 2026-05-28 | 2026-05-28 | 0 | 117 |  |  | 96 |  |  |  | 2026-06-22 | 2026-06-22 | 17 | Green
1 | Production Migration Phase I | Completed | 1 | 2026-05-19 | 2026-06-03 | 11 |  |  |  | 92 |  |  |  | 2026-05-19 | 2026-06-23 | 14 | Green
1 | Production Go-Live Phase I | Completed | 1 | 2026-06-08 | 2026-06-08 | 0 | 146 |  |  | 69 |  |  |  | 2026-06-24 | 2026-06-24 | 12 | Red
1 | Hypercare Phase I | In Progress | 0.25 | 2026-06-09 | 2026-07-06 | 20 | 147 | UniSan IT Team, UniSan Integration Team, UniSan Project Group, Zycus Consultant, Zycus Product Specialist |  | 69 |  |  |  | 2026-06-25 | 2026-07-23 | 13 | Red
1 | Configuration Validation & Documentation Phase II | In Progress | 0.26 | 2026-06-19 | 2026-07-22 | 24 |  |  |  | 57 | [6 empty] | Yellow
1 | eProc and eInvoice and Merlin APSD | In Progress | 0.21 | 2026-06-19 | 2026-08-04 | 33 |  |  |  | 48 | [6 empty] | Green
1 | Contract Management with Basic Setup Phase II | In Progress | 0.03 | 2026-07-14 | 2026-08-07 | 19 |  |  |  | 45 | [6 empty] | Red
1 | iSupplier Deployment | In Progress | 0.13 | 2026-06-12 | 2026-08-11 | 43 |  |  |  | 43 | [6 empty] | Red
2 | Design & Development on STAGING Set UP | In Progress | 0.13 | 2026-06-12 | 2026-08-11 | 43 |  |  |  | 43 | [6 empty] | Green
2 | Users,Roles,Workflow & View Definition Configuration | Not Started | 0 | 2026-07-22 | 2026-07-22 | 1 |  |  |  | 23 | [6 empty] | Red
2 | Pre-UAT on STAGING Set UP | In Progress | 0.05 | 2026-06-12 | 2026-07-22 | 29 |  |  |  | 57 | [6 empty] | Green
2 | Supplier Bulk Upload on STAGING | In Progress | 0.05 | 2026-06-12 | 2026-07-15 | 24 |  |  |  | 62 | [6 empty] | Red
3 | UniSan to provide supplier bulk upload data | In Progress | 0.5 | 2026-06-12 | 2026-06-12 | 1 | 260 | UniSan IT Project Manager, UniSan IT Team, UniSan Project Manager |  | 45 | [6 empty] | Red
3 | Zycus to review the files and provide feedback | In Progress | 0.5 | 2026-06-15 | 2026-06-15 | 1 | 263 | Zycus Product Specialist |  | 45 | [6 empty] | Red
3 | UniSan to provide updated bulk upload data | Not Started | 0 | 2026-06-23 | 2026-06-24 | 2 | 264 | UniSan IT Project Manager, UniSan IT Team, UniSan Project Manager |  | 45 | [6 empty] | Red
3 | Zycus to bulk upload supplier data on STAGING setup | Not Started | 0 | 2026-06-25 | 2026-06-26 | 2 | 265 | Zycus Product Specialist |  | 45 | [6 empty] | Red
3 | UniSan to review bulk uploaded data | Not Started | 0 | 2026-06-29 | 2026-07-01 | 3 | 266 | UniSan Core Project Team |  | 49 | [6 empty] | Red
3 | UniSan to sign off on supplier bulk upload | Not Started | 0 | 2026-07-01 | 2026-07-01 | 1 | 267 | UniSan Project Manager |  | 50 | [6 empty] | Red
3 | UniSan Prod migration Supplier | Not Started | 0 | 2026-07-02 | 2026-07-15 | 10 | 268 | Zycus Product Specialist |  | 50 | [6 empty] | Yellow
2 | Integration iSupplier | In Progress | 0.38 | 2026-06-25 | 2026-07-16 | 16 |  |  |  | 61 | [6 empty] | Green
3 | Integration Design | In Progress | 0.63 | 2026-06-25 | 2026-06-30 | 4 |  |  |  | 73 | [6 empty] | Red
4 | Mapping activity for Integration | Completed | 1 | 2026-06-25 | 2026-06-25 | 1 | 200 | UniSan Integration Team, Zycus Integration Specialist |  | 24 | [6 empty] | Green
4 | Share TDD for interface | Completed | 1 | 2026-06-26 | 2026-06-26 | 1 | 273 | Zycus Integration Lead |  | 27 | [6 empty] | Green
4 | Review of TDD and share feedback with Zycus | In Progress | 0.5 | 2026-06-29 | 2026-06-29 | 1 | 274 | UniSan Integration Team |  | 24 | [6 empty] | Red
4 | Sign off on TDD | Not Started | 0 | 2026-06-30 | 2026-06-30 | 1 | 275 | UniSan Integration Team |  | 27 | [6 empty] | Green
3 | Development and Testing on STAGING Set Up | In Progress | 0.29 | 2026-07-01 | 2026-07-16 | 12 |  |  |  | 61 | [6 empty] | Green
4 | Integration set up and development at Zycus | In Progress | 0.8 | 2026-07-06 | 2026-07-10 | 5 | 276 | Zycus Integration Specialist |  | 24 | [6 empty] | Green
4 | Integration development at UniSan - as applicable | Not Started | 0 | 2026-07-01 | 2026-07-07 | 5 | 276 | UniSan Integration Team |  | 24 | [6 empty] | Red
4 | Integration Unit Testing and Feedback Incorporation | Not Started | 0 | 2026-07-13 | 2026-07-14 | 2 | 278, 279 | Zycus Integration Team |  | 24 | [6 empty] | Green
4 | SIT on STAGING Set Up | Not Started | 0 | 2026-07-15 | 2026-07-16 | 2 | 280 | UniSan Integration Team, Zycus Integration Team |  | 23 | [6 empty] | Green
4 | Sign off on SIT | Not Started | 0 | 2026-07-16 | 2026-07-16 | 1 | 282 | UniSan Integration Team |  | 23 | [6 empty] | Green
1 | User Acceptance Testing (UAT) Phase II | Not Started | 0 | 2026-08-07 | 2026-08-24 | 12 |  |  |  | 34 | [6 empty] | Green
1 | UAT Completion | Not Started | 0 | 2026-08-24 | 2026-08-24 | 0 | 346, 349 |  |  | 24 | [6 empty] | Green
1 | Training Phase II | Not Started | 0 | 2026-08-18 | 2026-09-02 | 12 |  |  |  | 27 | [6 empty] | Green
1 | Production Migration Phase II | Not Started | 0 | 2026-08-21 | 2026-09-07 | 12 |  |  |  | 24 | [6 empty] | Green
1 | Production Go-Live Phase II | Not Started | 0 | 2026-09-11 | 2026-09-11 | 0 | 381 |  |  | 0 |  |  | TRUE |  |  |  | Green
1 | Hypercare Phase II | Not Started | 0 | 2026-09-14 | 2026-10-09 | 20 | 382 |  |  | 0 |  |  | TRUE |  |  |  | Green

## Dashboard
Project Name |  | UniSan S2P Implementation
Project Manager |  | Rajat Bothra
Project Start Date |  | 2026-02-11
Project End Date |  | 2026-10-09
Not Started |  | 175
In Progress |  | 35
Completed |  | 133
On Hold |  | 0
At Risk | High
Project Stage | Training Phase I
% Complete |  | 44%
Schedule Health | Red
Today's Date |  | 2026-07-02