## Project Plan
Level | Task Name | Status | % Complete | Start Date | End Date | Duration | Predecessors | Owner | Priority | Total Float | Critical ? | On Hold? | Not Applicable? | Baseline Start | Baseline Finish | Variance | Schedule Health | Comments | Assigned To
0 | Zycus - Titan S2P Implementation | In Progress | 0.71 | 2025-12-05 | 2026-12-07 | 262 |  |  |  | 0 | TRUE |  |  | 2026-05-03 | 2026-05-20 | -2 | Green
1 | Phase 1- S2C | In Progress | 0.92 | 2025-12-05 | 2026-07-14 | 158 |  | abhilasha.s@zycus.com |  | 104 |  |  |  | 2025-12-05 | 2026-07-02 | -6 | Yellow
1 | Phase 2 - P2P | In Progress | 0.21 | 2026-04-22 | 2026-12-07 | 164 |  |  |  | 0 |  |  |  | 2026-04-15 | 2026-08-10 | -81 | Yellow
2 | Project Initiation & Data Gathering | Completed | 1 | 2026-04-22 | 2026-06-02 | 30 |  |  |  | 134 |  |  |  | 2026-04-15 | 2026-04-30 | -15 | Yellow
3 | Zycus BootCamp | Completed | 1 | 2026-04-22 | 2026-04-23 | 2 |  |  |  | 162 | [6 empty] | Green
3 | Logistics Activities | Completed | 1 | 2026-05-18 | 2026-06-02 | 12 |  |  |  | 134 |  |  |  | 2026-04-15 | 2026-04-20 | -9 | Yellow
3 | Data Gathering & STAGING Set Up | Completed | 1 | 2026-04-28 | 2026-05-22 | 19 |  |  |  | 141 |  |  |  | 2026-04-15 | 2026-04-30 | -15 | Yellow
2 | Configuration Documentation workshop | In Progress | 0.25 | 2026-06-22 | 2026-07-13 | 16 |  |  |  | 105 |  |  |  | 2026-04-21 | 2026-05-26 | -43 | Yellow
3 | P2P, iSupplier Configuration Documentation Workshop | Completed | 1 | 2026-06-22 | 2026-06-26 | 5 |  | Titan Core Project Team, Titan Project Manager, Zycus Merlin Product Team, Zycus Project Manager |  | 88 |  |  |  | 2026-04-21 | 2026-05-04 | -22 | Yellow
3 | Master data to be provided by OTK team | Not Started | 0 | 2026-06-26 | 2026-07-02 | 5 |  | Titan Core Project Team | High | 88 | [6 empty] | Red
3 | Workflow details & CULT table details to be provided by OTK | Not Started | 0 | 2026-06-26 | 2026-07-10 | 11 | 106 | Titan Core Project Team |  | 0 | [6 empty] | Red
3 | Develop & Publish 1st draft of IAD for eProc-eInvoice | Not Started | 0 | 2026-07-07 | 2026-07-09 | 3 | 292, 293 | Zycus Consultant |  | 88 |  |  |  | 2026-05-12 | 2026-05-12 | -24 | Yellow
3 | eProc-eInvoice IAD Review and Sign off by Titan | Not Started | 0 | 2026-07-10 | 2026-07-13 | 2 | 295 | Titan Project Manager |  | 88 |  |  |  | 2026-05-13 | 2026-05-13 | -25 | Yellow
2 | P2P Integration Design | In Progress | 0.39 | 2026-06-29 | 2026-07-10 | 10 |  |  |  | 106 | [6 empty] | Yellow
3 | eInvoice outbound | In Progress | 0.9 | 2026-06-29 | 2026-06-29 | 1 |  |  |  | 115 |  |  |  | 2026-05-12 | 2026-05-19 | -22 | Yellow
3 | eProc Direct & Indirect | In Progress | 0.9 | 2026-06-30 | 2026-07-01 | 2 |  |  |  | 113 |  |  |  | 2026-05-12 | 2026-05-18 | -30 | Yellow
3 | Master data inbound | Not Started | 0 | 2026-07-07 | 2026-07-08 | 2 |  |  |  | 108 |  |  |  | 2026-05-12 | 2026-05-13 | -44 | Yellow
3 | Review and feedback incorporation | Not Started | 0 | 2026-07-09 | 2026-07-09 | 1 | 303 | Titan Integration Team, Titan Project Manager, Zycus Consultant, Zycus Integration Specialist |  | 89 | [6 empty] | Yellow
3 | Sign off on LLD | Not Started | 0 | 2026-07-10 | 2026-07-10 | 1 | 304 | Titan Project Manager |  | 89 | [6 empty] | Yellow
2 | Configuration and Build phase | Not Started | 0 | 2026-07-13 | 2026-09-03 | 39 |  |  |  | 67 | [6 empty] | Green
3 | User Roles configuration | Not Started | 0 | 2026-07-14 | 2026-07-15 | 2 | 296 |  |  | 88 | [6 empty] | Green
3 | Admin settings configuration | Not Started | 0 | 2026-07-16 | 2026-07-17 | 2 | 309 |  |  | 88 | [6 empty] | Green
3 | Configure Workflow | Not Started | 0 | 2026-07-20 | 2026-07-24 | 5 | 310 |  |  | 88 | [6 empty] | Green
2 | User Acceptance Testing (UAT) | Not Started | 0 | 2026-09-04 | 2026-10-20 | 33 |  |  |  | 34 | [6 empty] | Green
3 | Migration of Solution from UAT to PRODUCTION | Not Started | 0 | 2026-09-24 | 2026-10-09 | 12 |  |  |  | 41 |  |  |  | 2026-07-20 | 2026-08-05 | -41 | Yellow
3 | Training | Not Started | 0 | 2026-10-12 | 2026-10-20 | 7 |  |  |  | 34 |  |  |  | 2026-08-03 | 2026-08-07 | -38 | Yellow
2 | P2P Cutover | Not Started | 0 | 2026-10-12 | 2026-12-07 | 41 |  |  |  | 0 |  |  |  | 2026-07-13 | 2026-08-07 | -62 | Yellow
3 | First Go-Live communication to all suppliers | Not Started | 0 | 2026-10-12 | 2026-10-13 | 2 | 477 | Titan Project Team |  | 0 |  |  | TRUE | 2026-07-13 | 2026-07-13 | -59 | Yellow
3 | Close all requisitions/PO/invoices in existing system | Not Started | 0 | 2026-10-16 | 2026-10-22 | 5 | 485 | Titan Project Team |  | 0 |  |  | TRUE | 2026-08-06 | 2026-08-06 | -50 | Yellow
3 | Load delta master data via integration | Not Started | 0 | 2026-10-30 | 2026-11-05 | 5 | 487 | Titan Integration Team |  | 0 |  |  | TRUE | 2026-07-31 | 2026-08-03 | -63 | Yellow
3 | Go Live | Not Started | 0 | 2026-11-09 | 2026-11-09 | 1 |  |  |  | 20 |  |  |  | 2026-08-10 | 2026-08-10 | -61 | Yellow

## Dashboard
Project Name |  | Titan S2P Implementation
Project Manager |  | Aftab Hashambhai
Project Start Date |  | 2025-12-05
Project End Date |  | 2026-12-07
Not Started |  | 194
In Progress |  | 15
Completed |  | 255
On Hold |  | 3
At Risk | High
Project Stage | Configuration and Build phase
% Complete |  | 71%
Schedule Health | Green
Today's Date |  | 2026-07-02